## Summary
MERIT development progress
Generated 2026-10-27 13:40 from tracking/tasks.json
Phase | Tasks | Done | In progress | Not started | Deferred | Blocked | % complete (excl. deferred)
0 Project setup | 5 | 5 | 0 | 0 | 0 | 0 | 100%
1 Database foundation | 5 | 5 | 0 | 0 | 0 | 0 | 100%
2 Data model | 13 | 13 | 0 | 0 | 0 | 0 | 100%
3 Stored procedures | 13 | 13 | 0 | 0 | 0 | 0 | 100%
4 Domain and application | 7 | 7 | 0 | 0 | 0 | 0 | 100%
5 Web (Razor + htmx) | 16 | 16 | 0 | 0 | 0 | 0 | 100%
6 JSON API | 1 | 1 | 0 | 0 | 0 | 0 | 100%
7 Angular client | 11 | 11 | 0 | 0 | 0 | 0 | 100%
8 Worker | 4 | 4 | 0 | 0 | 0 | 0 | 100%
9 Tests | 5 | 5 | 0 | 0 | 0 | 0 | 100%
10 Later releases | 11 | 0 | 0 | 0 | 11 | 0 | 0%
10 Access model | 2 | 2 | 0 | 0 | 0 | 0 | 100%
11 Tenant management | 4 | 4 | 0 | 0 | 0 | 0 | 100%
12 Quality | 36 | 36 | 0 | 0 | 0 | 0 | 100%
ALL | 133 | 122 | 0 | 0 | 11 | 0 | 100%

## Tasks
ID | Phase | Task | Spec reference | Deliverable / location | Status | % complete | Started | Finished | Notes
T001 | 0 Project setup | Claude Code usage journal spreadsheet and refresh script | prompt.txt step 1 | journal/MERIT_ClaudeCode_Usage.xlsx | Done | 100% | 2026-10-24 | 2026-10-24
T002 | 0 Project setup | Task tracker spreadsheet (this file) generated from tasks.json | prompt.txt step 2 | tracking/MERIT_Task_Tracker.xlsx | Done | 100% | 2026-10-24 | 2026-10-24
T003 | 0 Project setup | Adapt SQL convention gate (validate-sql.py) to camelCase names and the renamed audit block (isDeleted, deletedBy, deletedDateUtc, createdBy, createdDateUtc, modifiedBy, modifiedDateUtc) | prompt.txt naming change | .claude/hooks/validate-sql.py | Done | 100% | 2026-10-24 | 2026-10-24
T004 | 0 Project setup | Solution skeleton: Merit.sln, Directory.Build.props (net9.0, nullable, warnings as errors, analyzers), Domain/Contracts/Application/Data.SqlServer/Web/Worker/Tests projects with layer references | Arch: Solution layout, R3, R5 | sourceCode/Merit.sln | Done | 100% | 2026-10-24 | 2026-10-25 | Merit.sln: Domain, Contracts, Application, Data.SqlServer, Web, Worker. Tests project not yet added.
T005 | 0 Project setup | README with build, deploy and run instructions | Adoption: project basics | sourceCode/README.md | Done | 100% | 2026-10-25 | 2026-10-25 | sourceCode/README.md: prerequisites, deploy, configure, build, run, demo users
T010 | 1 Database foundation | Database bootstrap: create database, schemas (dbo, auth, config, logs, util, logsData, history), util.uspSetObjectDescription | Skill: schema placement, rule 4 | sourceCode/database/000-009 | Done | 100% | 2026-10-24 | 2026-10-24
T011 | 1 Database foundation | Execution logging subsystem (logs.executionLog + four logging procedures) adapted to camelCase audit columns | Skill rule 8 | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T012 | 1 Database foundation | DDL change logging subsystem (record_db_changes trigger, history tables) adapted to camelCase audit columns | Skill rule 10 | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T013 | 1 Database foundation | Roles and schema permissions: applicationRole, workerRole, readOnlyRole; EXECUTE per procedure only | Spec: Stack (EXECUTE only); Arch: least privilege | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24 | meritWebRole and meritWorkerRole hold EXECUTE per procedure only; the skill's applicationRole/readOnlyRole are deliberately not created so no schema-level table grants reach the app logins.
T014 | 1 Database foundation | Re-runnable PowerShell deployment script (Deploy-MeritDatabase.ps1): creates DB if missing, runs scripts in order with sqlcmd -I -C -b, creates app/worker logins optionally, reports results | Deliverable 1 | sourceCode/database/Deploy-MeritDatabase.ps1 | Done | 100% | 2026-10-24 | 2026-10-24 | Deploy-MeritDatabase.ps1: -ServerInstance, -DatabaseName, -SqlCredential, -CreateLogins, -IncludeDemoData.
T020 | 2 Data model | Tenant tree: auth.tenant, auth.tenantClosure, auth.tenantJurisdiction; config.subJurisdiction (counties) | Spec: Tenant tree | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T021 | 2 Data model | Security tables: auth.appUser, auth.permission, auth.profile, auth.profilePermission, auth.userAssignment, auth.sessionScope, auth.sessionScopeTenant, auth.mfaRecoveryCode | Spec: Profiles and permissions; Authentication | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T022 | 2 Data model | Configuration: config.jurisdictionSetting (effective-dated), config.lookupValue (administrator lookups with extract codes) | Spec: Jurisdiction configuration; Entity definitions (enumerations) | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T023 | 2 Data model | Analytes: config.analyte, config.analyteSpecimen, config.acceptedUnit, config.loincCode, config.actionCode, config.threshold, config.confirmingMethod | Spec: Analytes, thresholds and result normalization | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T024 | 2 Data model | Person: dbo.person, personAlias, personRace, personContactMethod, personIdentifier, pregnancyEpisode, personRelationship, personAccess, personMatchKey | Spec: Person, Person alias, Pregnancy episode, Person relationship; Shared database | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T025 | 2 Data model | Places and organizations: dbo.organization, organizationType, location, organizationSite, locationOwner, personLocation, employment, employmentAnalyte, exposureSource, product, provider | Spec: Organization, Location, Person location, Employment, Exposure source, Provider | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T026 | 2 Data model | Results and intake: dbo.intakeBatch, intakeProfile, stagingRow, stagingHoldReason, labResult | Spec: Lab result; Intake pipeline; Held records | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T027 | 2 Data model | Cases and investigations: dbo.merCase, caseActivity, investigation, investigationCase, environmentalSample, config.environmentalStandard | Spec: Case, Investigation | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T028 | 2 Data model | Work: dbo.workTask (queues and cross-link tasks), cluster, caseCluster, dbo.jobQueue (per-tenant, row-lock claim) | Spec: Work queues, Cross-links, Cluster detection; Arch: Deployment shape | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T029 | 2 Data model | Audit: logs.auditEvent as append-only ledger table holding only IDs, actions, users and times | Spec: Security and audit; Shared database (ledger) | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T030 | 2 Data model | Federal extracts: config.extractLayout, config.extractLayoutField, dbo.extractRun | Spec: Federal extracts | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T031 | 2 Data model | Row-level security: predicate functions and security policies (filter + block) on tenant-owned tables; person predicate via personAccess; fail closed without session context | Spec: Row-level security | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24 | 37 tables under auth.tenantIsolationPolicy (filter + block after insert/update); predicates fail closed.
T032 | 2 Data model | Reference and demo seed data: permissions, shipped profiles, demo tenant tree (state, occupational program, two counties), analytes PB/HG/CD/AS, specimens, units, LOINC, CDC 3.5 child row, inactive federal rows, settings defaults, lookups, synthetic demo people | Spec: Adoption (reference data shipped, synthetic data) | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24 | 500_seed reference data + config.uspCreateRootTenant; 900_demo synthetic Maryland jurisdiction.
T040 | 3 Stored procedures | Session and security procs: sign-in lookup, resolve effective permissions and session scope, set session context, MFA enrollment, lockout | Spec: Row-level security 1, 5; Authentication | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T041 | 3 Stored procedures | Person procs: search, get page sections, save person, aliases, relationships, pregnancy episodes, contact methods, race | Spec: Person; UI Person page | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T042 | 3 Stored procedures | Place procs: save location (find existing), save person location with one-primary rule under row locks, set primary residence with row split, maintain personAccess | Spec: Address rules 1-3, 12; Person access table | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T043 | 3 Stored procedures | Organization, employment, exposure source and provider procs | Spec: Organization, Employment, Exposure source, Provider | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T044 | 3 Stored procedures | Lab result procs: lookups for cascading form, save result, duplicate/supersede detection, results by person | Spec: Lab result; Result entry form | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T045 | 3 Stored procedures | Case procs: open/attach case, classification update with override reason, activities, close with reason | Spec: Case; Case classification | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T046 | 3 Stored procedures | Investigation procs: find open investigation for target, create, link cases, status, environmental samples with computed exceedance | Spec: Investigation | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T047 | 3 Stored procedures | Work queue and task procs: queue counts, paged queue lists, assign, complete | Spec: Work queues | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T048 | 3 Stored procedures | Intake procs: create batch, staging rows, hold reasons, release/reject, held queue grouped by cause | Spec: Intake pipeline; Held records | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T049 | 3 Stored procedures | Job queue procs: enqueue, claim with UPDLOCK/READPAST, complete, fail with back-off, queue depth per tenant | Arch: Deployment shape rules 1-2, 8 | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T050 | 3 Stored procedures | Configuration procs: thresholds, settings, analytes (admin screens) | Spec: Jurisdiction configuration | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T051 | 3 Stored procedures | Audit proc: record view/change/export events | Spec: Security and audit | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T052 | 3 Stored procedures | Extract procs: CBLS and ABLES source rows, extract run status | Spec: Federal extracts | sourceCode/database | Done | 100% | 2026-10-24 | 2026-10-24
T060 | 4 Domain and application | Domain: population derivation (DOB, pregnancy episodes, adult cutoff, 42-week default) | Spec: Population derivation | src/Merit.Domain | Done | 100% | 2026-10-25 | 2026-10-25
T061 | 4 Domain and application | Domain: result normalization (operator parse, unit multiplier, below-detection indeterminate rule, creatinine adjustment) | Spec: Intake normalization | src/Merit.Domain | Done | 100% | 2026-10-25 | 2026-10-25
T062 | 4 Domain and application | Domain: threshold evaluation and child/adult/other-metal classification (venous/capillary, confirming methods, 12-week rule, arsenic speciation task) | Spec: Case classification | src/Merit.Domain | Done | 100% | 2026-10-25 | 2026-10-25
T063 | 4 Domain and application | Domain: primary residence rules (overlap check, row split plan, county change preview) | Spec: Address rules 1-3, 6, 12 | src/Merit.Domain | Done | 100% | 2026-10-25 | 2026-10-25
T064 | 4 Domain and application | Domain: identifier checks (NPI Luhn with 80840 prefix, CLIA format), time-ordered UUID generator | Spec: Provider; Shared database keys | src/Merit.Domain | Done | 100% | 2026-10-25 | 2026-10-25
T065 | 4 Domain and application | Application services: people, places, results (save + classify), cases, investigations, queues, intake, config, extracts, accounts; permission checks | Arch: MVC rules 1, 4 | src/Merit.Application | Done | 100% | 2026-10-25 | 2026-10-25
T066 | 4 Domain and application | Data access: Dapper repositories calling stored procedures; per-connection sp_set_session_context (read-only) for RLS | Spec: Stack; RLS 1, 5 | src/Merit.Data.SqlServer | Done | 100% | 2026-10-25 | 2026-10-25
T070 | 5 Web (Razor + htmx) | Host: AddControllersWithViews, cookie auth (Secure, HttpOnly, SameSite=Strict), fallback auth policy, permission policies, antiforgery X-XSRF-TOKEN, CSP with nonce, request-context middleware, health endpoint | Arch: ASP.NET Core host; Security across both front ends | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T071 | 5 Web (Razor + htmx) | Static assets: USWDS 3 CSS/fonts/icons (no USWDS JS), htmx 4.0.0 served from origin, merit.js (antiforgery header, focus/aria-live handling) | Arch: htmx requirements (Delivery, Scripts and CSP, Accessibility) | src/Merit.Web/wwwroot | Done | 100% | 2026-10-25 | 2026-10-25
T072 | 5 Web (Razor + htmx) | Shared layout, header/navigation, alert region, HtmxResult helper (HX-Request-Type partial vs full), 422 validation partials, HX-Retarget/HX-Redirect handling | Arch: One action, two shapes; Inheritance, swaps and errors | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T073 | 5 Web (Razor + htmx) | Sign-in and account pages: password sign-in with lockout, TOTP MFA enrollment and verification, recovery codes, sign-out | Spec: Authentication (built-in accounts) | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T074 | 5 Web (Razor + htmx) | Home dashboard with queue count tiles that poll a partial | Arch: Screen assignments | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T075 | 5 Web (Razor + htmx) | Global search (name, DOB, accession, case number) | Spec: UI General | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T076 | 5 Web (Razor + htmx) | Person page: header, sections ordered by population, each section a partial that reloads after its own edit, empty states, server-rendered SVG trend chart | Spec: Person page; Arch: Screen assignments | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T077 | 5 Web (Razor + htmx) | Places: add residence/other place, overlapping residence requires primary choice, Set as primary dialog with row split and county change preview | Spec: Places behavior | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T078 | 5 Web (Razor + htmx) | Relationships, employment, exposure sources, pregnancy episodes editors on the person page | Spec: Person page sections | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T079 | 5 Web (Razor + htmx) | Result entry form with cascading drop-downs and save summary (canonical value, thresholds crossed, case outcome) | Spec: Result entry form | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T080 | 5 Web (Razor + htmx) | Case page: classification, override with reason, activities log, close with reason, linked investigations | Spec: Case; workflows | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T081 | 5 Web (Razor + htmx) | Investigation page: target, status, dates, findings, regulatory action, environmental samples | Spec: Investigation | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T082 | 5 Web (Razor + htmx) | Configuration screens: thresholds, jurisdiction settings, analytes | Spec: Jurisdiction configuration | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T083 | 5 Web (Razor + htmx) | Intake upload (CSV) creating a job; batch status card polls a partial | Spec: Intake formats; Arch: Long work runs in the worker | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T084 | 5 Web (Razor + htmx) | Federal extracts screen: request run, status cards poll, download file | Arch: Screen assignments (Federal extracts) | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T085 | 5 Web (Razor + htmx) | Server-side type-ahead (organization, provider) following ARIA combobox pattern | Arch: Dates and type-ahead | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25
T090 | 6 JSON API | API controllers under /api/v1 ([ApiController]) for queues, held records, results, persons; RFC 9457 problem details; OpenAPI document | Arch: ASP.NET Core host | src/Merit.Web/Controllers/Api | Done | 100% | 2026-10-25 | 2026-10-25
T100 | 7 Angular client | Angular 22 workspace under /app/: strict TS, strictTemplates, standalone components, signals, OnPush, lazy routes, bundle budgets, XSRF config, CSP nonce | Arch: Angular requirements | src/Merit.Web/ClientApp | Done | 100% | 2026-10-25 | 2026-10-25 | Angular 22.2.3 zoneless workspace, strict, lazy routes, budgets, XSRF, ngCspNonce; builds clean
T101 | 7 Angular client | Razor host view for /app/ routes with shared header, antiforgery cookie and ngCspNonce | Arch: Angular requirements (Hosting) | src/Merit.Web | Done | 100% | 2026-10-25 | 2026-10-25 | Views/AppHost/Index.cshtml; APP_BASE_HREF /app/; verified in headless Edge
T102 | 7 Angular client | API client and contract types for the endpoints the Angular screens use | Arch: API client | ClientApp/src/app/api | Done | 100% | 2026-10-25 | 2026-10-25 | api/contracts.ts + api-client.ts; all 13 endpoints smoke-tested
T103 | 7 Angular client | Shared CDK data grid: server-side paging, sorting, filtering, bulk selection, column chooser | Spec: Front end (data-heavy screens) | ClientApp/src/app/shared/grid | Done | 100% | 2026-10-25 | 2026-10-25 | shared/grid/data-grid.component.ts (CDK table)
T104 | 7 Angular client | Work queues screen (tasks by queue, assign/complete in bulk) | Spec: Work queues | ClientApp/src/app/features/queues | Done | 100% | 2026-10-25 | 2026-10-25 | features/queues; renders live data in headless Edge
T105 | 7 Angular client | Held records screen grouped by reason; release / reject with reason | Spec: Held records | ClientApp/src/app/features/held | Done | 100% | 2026-10-25 | 2026-10-25 | features/held; groups by cause, release/reject, corrections
T106 | 7 Angular client | Results list (line list) with filters | Arch: Screen assignments | ClientApp/src/app/features/results | Done | 100% | 2026-10-25 | 2026-10-25 | features/results; server-side filters, sort, paging
T107 | 7 Angular client | MSBuild integration: npm ci + ng build on Release/first build, output to wwwroot/app | Deliverable 2 | src/Merit.Web/Merit.Web.csproj | Done | 100% | 2026-10-25 | 2026-10-25 | BuildAngularClient target: npm install + ng build on first/Release build
T108 | 7 Angular client | Person matching review screen (side by side, keyboard-driven) | Spec: Person matching review | ClientApp | Done | 100% | 2026-10-25 | 2026-10-25 | Angular /app/match-review: queue, side-by-side field comparison (agree/close/different/missing), ranked candidates, one-line reasons, twin/placeholder safeguards, history panel, keys 1-5 S D N C H J K; remembered Different person (dbo.matchExclusion); Not sure -> matchReview queue
T109 | 7 Angular client | Person timeline, maps and cluster review | Arch: Screen assignments | ClientApp | Done | 100% | 2026-10-25 | 2026-10-25 | Timeline plus /app/map (SVG zoom/pan case map, no tiles) and /app/clusters review (status, notes, join/leave, member map)
T110 | 7 Angular client | Reports and analytics with interactive charts | Spec: Reports and analytics | ClientApp | Done | 100% | 2026-10-25 | 2026-10-25 | /app/reports: 5 standard reports (testing counts, elevated cases, case timeliness, investigation outcomes, reporter timeliness), measure picker charts, table view, CSV/Excel export (data.export, audited). Query builder and analytics DB remain T146
T120 | 8 Worker | Merit.Worker: job claim loop, per-job session context for tenant/user, retry with back-off, health endpoint, queue depth | Arch: Deployment shape | src/Merit.Worker | Done | 100% | 2026-10-25 | 2026-10-25
T121 | 8 Worker | Intake job: parse CSV with an intake profile, validate, normalize, match (exact match key), commit or hold with reasons, classify | Spec: Intake pipeline | src/Merit.Worker | Done | 100% | 2026-10-25 | 2026-10-25
T122 | 8 Worker | Extract job: CBLS and ABLES files from configured layout, validation report | Spec: Federal extracts | src/Merit.Worker | Done | 100% | 2026-10-25 | 2026-10-25
T123 | 8 Worker | Cluster detection job (shared location / worksite within window) | Spec: Cluster detection | src/Merit.Worker | Done | 100% | 2026-10-25 | 2026-10-25
T130 | 9 Tests | Unit tests: population, normalization, classification, residence rules, NPI/CLIA | Arch: Testing (unit) | tests/Merit.Tests | Done | 100% | 2026-10-25 | 2026-10-25 | tests/Merit.Tests: population, normalization, keys, NPI/CLIA, ids, classification, residence, TOTP RFC vectors
T131 | 9 Tests | Architecture tests: layer rules (controllers do not reference data project, domain references nothing, view models free of domain types) | Arch: MVC rule 6 | tests/Merit.Tests | Done | 100% | 2026-10-25 | 2026-10-25 | NetArchTest: domain pure, application no data/web, web no SQL, controllers no I*Data
T132 | 9 Tests | Endpoint inventory test: every action has a permission policy | Arch: Testing (endpoint inventory) | tests/Merit.Tests | Done | 100% | 2026-10-25 | 2026-10-25 | EndpointInventoryTests: every action has HTTP method and a known policy; anonymous allow-list
T133 | 9 Tests | Database deployment verified twice against SQL Server 2022 (re-runnable) and convention gate passes | Deliverable 1; Skill rule 7 | sourceCode/database | Done | 100% | 2026-10-25 | 2026-10-25 | Deployed from scratch and re-run cleanly on localhost\PORTAL; validate-sql gate passes
T134 | 9 Tests | Integration tests with WebApplicationFactory + SQL Server container; cross-tenant RLS suite; Playwright + axe end-to-end | Arch: Testing and quality gates | tests | Done | 100% | 2026-10-25 | 2026-10-25 | tests/Merit.IntegrationTests (WebApplicationFactory, real SQL Server MERIT_IT deployed by the suite; no Docker on this machine, MERIT_IT_SERVER points at a container): pages full+partial, API reads, anonymous inventory, cross-tenant HTTP + every-procedure suite with leak self-check (12 pass). tests/e2e Playwright 1.64 + axe 4.13, Edge, tablet, WCAG 2.1 AA + keyboard flows (22 pass). Found and fixed: search duplicate-row error, intake Apt/unit field collision, table-wrap and SVG ARIA issues
T140 | 10 Later releases | HL7 v2.5.1 / v2.3.1 ORU^R01 parsers with acknowledgments; eICR parser | Spec: Intake formats |  | Deferred | 0% |  |  | Parser plug-in interface exists; parsers not built in this release.
T141 | 10 Later releases | Intake profile builder screen (sample upload, mapping suggestions, preview, header-signature drift pause, versioning) | Spec: Intake profiles |  | Deferred | 0%
T142 | 10 Later releases | Probabilistic matching with presets, plain-language rules and test-before-save; merge with preview and undo | Spec: Person matching; Matching configuration |  | Deferred | 0% |  |  | This release links on exact normalized name + DOB and sends others to review.
T143 | 10 Later releases | NPPES NPI Registry and CMS CLIA lookups, cache and refresh job | Spec: Provider and laboratory reference data |  | Deferred | 0%
T144 | 10 Later releases | Microsoft Entra ID (OpenID Connect) sign-in and SCIM provisioning; FIDO2/passkeys for administrators | Spec: Authentication |  | Deferred | 0%
T145 | 10 Later releases | Geocoding, census tract, map views, distance-based clusters | Spec: Location; Cluster detection |  | Deferred | 0%
T146 | 10 Later releases | Per-root-tenant analytics database, de-identified views, query builder, report library | Spec: Reports and analytics |  | Deferred | 0%
T147 | 10 Later releases | Custom fields, letters and templates, reporter registry cadence alerts, completeness dashboard, product registry screens | Spec: Problems other jurisdictions report |  | Deferred | 0%
T148 | 10 Later releases | Workflow templates engine with configurable steps and closure criteria; cross-link task generation for all trigger types | Spec: Investigation workflows |  | Deferred | 0% |  |  | This release creates the default workflow tasks in code.
T149 | 10 Later releases | Per-tenant export and purge procedures; temporal history tables with their own RLS policies | Spec: Shared database |  | Deferred | 0%
T150 | 10 Later releases | Container images and deployment manifests for web and worker | Arch: Deployment shape rule 6 |  | Deferred | 0%
T160 | 10 Access model | Hierarchical tenant authorization: platform/region/state/tribe/jurisdiction tree, roles (renamed from profiles), master profile + user-made profiles with switching, per-tenant read/write/full via RLS write predicates, tree-scoped administration, view-as, platform administrator with no record access | Request 2026-10-25 | database, Merit.Application, Merit.Web, tests | Done | 100% | 2026-10-25 | 2026-10-25 | Migration 060 (profile->role rename, tenant types, policy v2), RLS write predicates, uspCreateSessionScope v2 (profiles, view-as, acting tenant), scoped admin procs, uspSaveMyProfile/ListMyProfiles/ListViewAsUsers/FindUserForGrant, platform tenant + first platform admin (deploy param), /account/profiles UI, admin UI home tenant/access level/view-as; AuthorizationScenarioTests (10) on EPA Region 3; all 108 .NET + 24 e2e tests pass
T161 | 10 Access model | User guide (PDF): who sees what, profiles and switching, with mock-up screens (EPA Region 3 example) | Request 2026-10-25 | docs | Done | 100% | 2026-10-25 | 2026-10-25 | docs/MERIT User Guide - Access and Profiles.pdf (12 pages; source docs/guides/access-guide.html)
T162 | 11 Tenant management | Add tenants: tenant.create permission, checked wrappers over owner-run installers, Tenants screen with session refresh | Request 2026-10-25 | config.uspCreateRoot/ChildTenant, /admin/tenants | Done | 100% | 2026-10-25 | 2026-10-25 | Platform admin anywhere; region admin states/tribes under region; Administrator role programs/jurisdictions; user administrator refused. Unit, scenario and e2e tests.
T163 | 11 Tenant management | Reporter registry: laboratories, facilities, providers; one-entry add/correct; checked CSV import of NPI and CLIA records | Request 2026-10-25 | /reporters, dbo.uspListReporters, dbo.uspImportReporters | Done | 100% | 2026-10-25 | 2026-10-25 | registry.edit for intake clerk, supervisor, administrator; sample samples/registry_npi_clia_sample.csv
T164 | 11 Tenant management | Extracts: View findings dialog and Mark submitted; quarter label fix and default to the last completed quarter | Request 2026-10-25 | /extracts, dbo.uspMarkExtractSubmitted | Done | 100% | 2026-10-25 | 2026-10-25 | extract.submit
T165 | 11 Tenant management | User guides: Daily Operations and Importing NPI and CLIA Records (PDF), three Archify workflow diagrams, access guide and README updates | Request 2026-10-25 | docs | Done | 100% | 2026-10-25 | 2026-10-25 | Real screenshots in docs/images/guide; sources in docs/guides
T166 | 12 Quality | Retake the user guide screenshots after the #3 fixes; print every image at one scale with whole-element crops; add the capture, sizing and print tools | Request 2026-10-26 | docs/guides, docs/images/guide | Done | 100% | 2026-10-26 | 2026-10-26 | PR #5; Daily Operations 26 pages, NPI/CLIA 8 pages
T167 | 12 Quality | Code review of sourceCode: verify findings and log them as GitHub issues with recommendations | Request 2026-10-26 | GitHub issues #6-#21 | Done | 100% | 2026-10-26 | 2026-10-26 | 16 issues: 3 security (#6 county mapping, #7 job session scope, #8 sign-in rate limit), 8 bugs, 1 performance, 4 UI/maintainability
T168 | 12 Quality | Issue #6: below the data root a new tenant serves only its parent's counties; new counties only under the root (enforced in config.uspInstallChildTenant for every caller) | GitHub issue #6 | procs_setup.py, Tenants screen, AuthorizationScenarioTests | Done | 100% | 2026-10-26 | 2026-10-26 | Scenario test BelowTheDataRootANewTenantServesOnlyItsParentsCounties; form lists only the parent's counties
T169 | 12 Quality | Issue #7: background jobs run under the queuing session's profile, view-as and acting tenant (stored on dbo.jobQueue; JobSessions.OpenAsync) | GitHub issue #7 | jobQueue, enqueue procedures, JobWorker, JobSessions | Done | 100% | 2026-10-26 | 2026-10-26 | Scenario test ABackgroundJobKeepsTheProfileAndTenantOfTheSessionThatQueuedIt; JobSessionTests
T170 | 12 Quality | Issue #8: sign-in rate limits per client address (sliding window; password and code steps counted separately), Too many attempts page with Retry-After, configurable limits, trusted reverse proxies for X-Forwarded-For | GitHub issue #8 | sourceCode/src/Merit.Web/Infrastructure/SignInRateLimits.cs | Done | 100% | 2026-10-26 | 2026-10-26 | SignInRateLimitTests: one client over the limit does not hold up another; rejected forms count
T171 | 12 Quality | Issue #14: intake registry lookups by index seek and once per batch: identifier-first filtered indexes on organization CLIA/NPI and provider NPI, uspResolveOrganization and uspImportReporters try CLIA then NPI then name, new uspGetProviderByNpi, RegistryLookups cache in IntakeProcessor | GitHub issue #14 | organization, provider, uspResolveOrganization, uspImportReporters, uspGetProviderByNpi, RegistryLookups | Done | 100% | 2026-10-26 | 2026-10-26 | RegistryLookupTests; scenario test RegistryLookupsTryTheCliaNumberThenTheNpiThenTheName; 100k-row check: 8,694 to 6 logical reads (CLIA), 8,155 to 3 (NPI)
T172 | 12 Quality | Issue #9: a chosen held group lists only its own rows: uspListHeldRows takes the sender and an exact-group flag (null value or sender means none), held groups carry the sender's id, the held page asks for the exact group and shows it above the grid | GitHub issue #9 | uspListHeldRows, IntakeService.HeldRowsAsync, api/v1/held/rows, held.page.ts | Done | 100% | 2026-10-26 | 2026-10-26 | HeldRecordsTests: two senders sharing a cause and value; follow-up issue #29 (uspCreateWorkTask cross-tenant references) found on the way
T173 | 12 Quality | Issue #29: uspCreateWorkTask refuses links to records the caller cannot see (51404); the cross-tenant suite aims at real records only (seeded staging row and cluster, no random-id fallback) and checks every write for hidden ids stored in the caller's own rows | GitHub issue #29 | uspCreateWorkTask, CrossTenantTests.cs | Done | 100% | 2026-10-26 | 2026-10-26 | ATaskCanLinkOnlyRecordsTheCallerCanSee; the suite reproduced the gap on every run before the fix
T174 | 12 Quality | Issue #12: one NPI and CLIA normalization (spaces and hyphens removed, CLIA upper case) shared by the registry and intake | GitHub issue #12 | ProviderIdentifiers, RegistryService, IntakeProcessor | Done | 100% | 2026-10-26 | 2026-10-26 | ProviderIdentifierTests
T175 | 12 Quality | Issue #11: one organization per CLIA number and per NPI: file check by identifier whatever the type, import groups shared identifiers into one organization, uspSaveOrganization refuses duplicates, unique indexes (generateTables dropIndexes) | GitHub issue #11 | RegistryService.CheckFile, uspImportReporters, uspSaveOrganization, dbo.organization | Done | 100% | 2026-10-26 | 2026-10-26 | RegistryCheckTests; OneImportMakesOneOrganizationPerIdentifier
T176 | 12 Quality | Issue #10: held-row corrections merge as a patch on the server; the page sends only changed fields and refreshes the open row | GitHub issue #10 | uspSaveStagingCorrection, held.page.ts | Done | 100% | 2026-10-26 | 2026-10-26 | HeldRecordsTests.ASecondCorrectionKeepsTheFirst
T177 | 12 Quality | Issue #15: Reporters filter is a plain text input (role searchbox), USWDS search-box override removed | GitHub issue #15 | Views/Reporters/Index.cshtml, merit.css | Done | 100% | 2026-10-26 | 2026-10-26 | e2e layout.spec.ts
T178 | 12 Quality | Issue #16: batch card file names break after underscores, dots and hyphens; card headings wrap anywhere as a last resort | GitHub issue #16 | Views/Intake/_Batches.cshtml, merit.css | Done | 100% | 2026-10-26 | 2026-10-26 | e2e layout.spec.ts
T179 | 12 Quality | Issue #13: Case timeliness report counts only follow-up activity types and reports cases not followed up yet | GitHub issue #13 | uspReportCaseTimeliness, ReviewServices | Done | 100% | 2026-10-26 | 2026-10-26 | CaseTimelinessCountsOnlyFollowUpWork
T180 | 12 Quality | Issue #19: Search results show open cases as linked case chips (shared _CaseChip partial with the person header); uspSearch returns them as JSON | GitHub issue #19 | uspSearch, Views/Search/_Results.cshtml, Views/Shared/_CaseChip.cshtml | Done | 100% | 2026-10-26 | 2026-10-26 | EndpointTests.SearchShowsOpenCasesAsChipsLinkingToTheCase
T181 | 12 Quality | Issue #17: Extract run card actions in their own row; Download label breaks file names after underscores (FileNames.Breakable) | GitHub issue #17 | Views/Extracts/_Runs.cshtml, merit.css, FileNames.cs | Done | 100% | 2026-10-26 | 2026-10-26 | e2e layout.spec.ts
T182 | 12 Quality | Issue #18: Row and grid forms no longer capped at 20rem; Reporters add form in columns, showing only the chosen kind's fields | GitHub issue #18 | merit.css, Views/Reporters/Index.cshtml | Done | 100% | 2026-10-26 | 2026-10-26 | e2e layout.spec.ts
T183 | 12 Quality | Issue #20: intake refuses a file already received for the same profile (contentSha256 on intakeBatch, uspFindIntakeBatchByContent) unless marked as a genuine re-send; 20 MB limit measured in bytes | GitHub issue #20 | intakeBatch, uspCreateIntakeBatch, IntakeService, Intake page | Done | 100% | 2026-10-26 | 2026-10-26 | IntakeUploadTests
T184 | 12 Quality | Issue #21: one SessionRenewal for sign-in, profile, view-as and tenant refresh; Session:LifetimeHours; ProfileId and ViewAsUserId on ICurrentSession | GitHub issue #21 | SessionRenewal.cs, Account/Profiles/Tenants controllers | Done | 100% | 2026-10-26 | 2026-10-26 | EndpointTests.ASessionRenewalReplacesTheScopeWithTheConfiguredLifetime
T185 | 12 Quality | Guide screenshots retaken on a fresh MERIT_GUIDES demo, guide text updated for #10-#13, #18-#20, Daily Operations and NPI/CLIA PDFs reprinted; card lists keep their width | User guides | docs/guides, docs/images/guide, merit.css | Done | 100% | 2026-10-26 | 2026-10-26 | Capture recipe in docs/guides/README.md
T186 | 12 Quality | Issue #26: intake profile picker shows the version number (explicit Razor expression); the page render test fails on any unrendered Razor | GitHub issue #26 | Views/Intake/Index.cshtml, EndpointTests | Done | 100% | 2026-10-26 | 2026-10-26 | Check flags /intake on the old view and no other page
T187 | 12 Quality | UX review of the running application (34 screens at 1280 and 390 px, three roles, forms, errors, axe): 16 issues filed, #36 to #51 | GitHub issues #36-#51 | Issues labelled ux; screenshots on the issue-assets branch (ux_review/) | Done | 100% | 2026-10-26 | 2026-10-26 | axe: no violations at 1280 px; main findings: UTC dates, raw codes, phone layout, first sign-in not recorded
T188 | 12 Quality | Dates and "today" in the jurisdiction's time zone, not UTC | Issue #36 | auth.tenant.timeZone; JurisdictionClock (IClock); auth.udfSessionToday; session claim merit:tz; DisplayTime; /api/v1/me timeZone | Done | 100% | 2026-10-27 | 2026-10-27 | Tenant form picks the zone; SQL today via session context; default Eastern
T189 | 12 Quality | Codes and file fields shown as words on the result pages and the Angular client | Issues #37, #38 | DisplayNames; GET /api/v1/reference/labels; Angular Display service; Results/Details field labels | Done | 100% | 2026-10-27 | 2026-10-27 | Lookup display names, analytes, system codes and staging field labels in one place
T190 | 12 Quality | One date format in the Angular client; case numbers and dates stay on one line | Issue #39 | Display.date/dateOf/month; GridColumn.nowrap; merit-nowrap in Razor lists | Done | 100% | 2026-10-27 | 2026-10-27 | e2e: no line breaks inside case numbers or dates, no ISO dates in the queue
T191 | 12 Quality | Home names each urgent held record and links to its batch | Issue #40 | uspGetDashboard held rows; Home view; IntakeProcessor message | Done | 100% | 2026-10-27 | 2026-10-27 | Title is person and analyte with value; "Held at intake from <sender>"
T192 | 12 Quality | Queue bulk assign waits for a chosen person and names them | Issue #41 | features/queues/queues.page.ts | Done | 100% | 2026-10-27 | 2026-10-27 | List starts on "Choose a person..."; Assign disabled until chosen; message names the assignee
T193 | 12 Quality | Unknown addresses and other status codes show a MERIT page | Issue #43 | HomeController.Status; UseStatusCodePagesWithReExecute outside /api | Done | 100% | 2026-10-27 | 2026-10-27 | 404, 403, 405/415 and 5xx pages; all methods, no antiforgery on the status page
T194 | 12 Quality | First sign-in after enrolment is recorded | Issue #44 | AccountService.CompleteEnrollmentAsync; Users page shows Never | Done | 100% | 2026-10-27 | 2026-10-27 | Integration test FirstSignInTests
T195 | 12 Quality | Phone width: Menu button, usable search, no sideways scroll | Issue #47 | _Layout header; merit.css; merit.js; queues, reports and cluster layouts | Done | 100% | 2026-10-27 | 2026-10-27 | e2e at 390 px: header folds, no main page wider than the screen
T196 | 12 Quality | Required fields marked; server errors shown as a USWDS error summary on Add a person and Enter a result | Issue #46 | FormErrors; _ErrorSummary; _PersonForm; _ResultForm; _ResultFields; _Combobox; merit.js | Done | 100% | 2026-10-27 | 2026-10-27 | Forms novalidate; summary in form order, linked and focused; result page post kept its errors; nonce bug found and logged as #53
T197 | 12 Quality | Focus ring hidden on script-focused headings for mouse users | Issue #51 | merit.css [tabindex=-1]:focus:not(:focus-visible) | Done | 100% | 2026-10-27 | 2026-10-27 | Keyboard focus keeps the ring
T198 | 12 Quality | Timeline axis labelled by span: years, months or days; no two-digit year | Issue #49 | features/timeline/timeline.page.ts axisTicks | Done | 100% | 2026-10-27 | 2026-10-27 | e2e checks label shape against the visible range
T199 | 12 Quality | CSP nonce in base64url, so htmx partials keep their htmx attributes | Issue #53 | Infrastructure/Htmx.cs CspNonce | Done | 100% | 2026-10-27 | 2026-10-27 | A '+' was HTML-encoded in hx-nonce and hx-csp stripped about one partial in three; unit and integration tests added
T200 | 12 Quality | Held rows held for an uncertain match link to Match review; Release skips them | Issue #42 | HeldRowDto.ReasonCodes; features/held; features/match-review ?row= | Done | 100% | 2026-10-27 | 2026-10-27 | Release disabled with an explanation when only such rows are selected
T201 | 12 Quality | Audit log: filters, paging, words, record links, CSV export | Issue #45 | logs.uspSearchAuditEvents; logs.uspListAuditUsers; AuditText; Views/Admin/Audit; _AuditLink | Done | 100% | 2026-10-27 | 2026-10-27 | Filters by user, action, record type, dates, record; 100 a page; export audited; links from person, case and result pages